## Sheet1
|  | a | Writing The Analysis Routines
|  | b | Conducting the 2 Meduim Sized Simulations
|  | c | Data Analysis on the Fisrt Set of Results
|  | d | Conducting the 1 big Sized Simulation
|  | r | Data Analysis on the second Set of Results
|  | f | Thesis Write Up
ID | Task Name | Predecessors | Duration | Jul,2011 | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun,2012
1 | Start |  | 0 days
2 | a | 1 | 90 days
3 | b | 2 | 60 days
4 | c | 3 | 60 days
5 | d | 4 | 30 days
6 | e | 5 | 30 days
7 | f | 6 | 90 days
8 | Finish | 7 | 0 days